## Sheet1
Application | # | Module | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Library Management System | 1 | Registration | Analysis | Requirement Analysis | 1.8 | 2017-11-01 | 2017-11-01 | 1.8 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2017-11-01 | 2017-11-01 | 2.4 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2017-11-02 | 2017-11-02 | 0.8 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Pratik Potdar | N/A
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Priyanka Chaudhary | N/A
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pradnya Shukla | N/A
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Rahul Vishwakarma | N/A
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Priyanka Chaudhary | N/A
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 |  | 2017-11-04 | 2017-11-04 | Pratik Potdar | N/A
|  |  | Build | Coding | 6 | 2017-11-04 | 2017-11-04 | 7 | 2017-11-04 | 2017-11-04 | Naveen Gownivaripalli | Completed
|  |  |  | Code Self Review | 2.5 | 2017-11-04 | 2017-11-04 | 2.5 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Self Testing | 6 | 2017-11-05 | 2017-11-05 | 7 | 2017-11-05 | 2017-11-05 | Pradnya Shukla | Completed
|  |  |  | Rework | 1.5 | 2017-11-05 | 2017-11-05 | 1.5 | 2017-11-05 | 2017-11-05 | Rahul Vishwakarma | Completed
|  |  |  | Code Peer Review | 1 | 2017-11-05 | 2017-11-05 | 1 | 2017-11-05 | 2017-11-05 | Naveen Gownivaripalli | Completed
|  |  |  | Peer Testing | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Priyanka Chaudhary | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Rahul Vishwakarma | Completed
|  |  |  | Rework | 1 | 2017-11-06 | 2017-11-06 | 1.5 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 4 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 1.5 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 3 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 1 | 2017-11-08 | 2017-11-08 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Total Planned Hrs : | 55.6 |  | Total Actual Hrs: | 38.2 |  |  |  | Completed
Library Management System | 2 | Login | Analysis | Requirement Analysis | 2.4 | 2017-11-01 | 2017-11-01 | 1.8 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.1 | 2017-11-01 | 2017-11-01 | 2.1 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.8 | 2017-11-01 | 2017-11-01 | 1.8 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.9 | 2017-11-02 | 2017-11-02 | 1 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 | 12 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 | 12 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 | 1.5 | 2017-11-03 | 2017-11-03 | Priyanka Chaudhary | Completed
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 | 0.5 | 2017-11-03 | 2017-11-03 | Rahul Vishwakarma | Completed
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 | 0.8 | 2017-11-03 | 2017-11-03 | Aditi Dumbre | Completed
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 | 0.5 | 2017-11-04 | 2017-11-04 | Pradnya Shukla | Completed
|  |  | Build | Coding | 11 | 2017-11-04 | 2017-11-04 | 13 | 2017-11-04 | 2017-11-04 | Naveen | Completed
|  |  |  | Code Self Review | 5 | 2017-11-04 | 2017-11-04 | 4 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Self Testing | 5 | 2017-11-05 | 2017-11-05 | 5 | 2017-11-05 | 2017-11-05 | Pratik Potdar | Completed
|  |  |  | Rework | 3 | 2017-11-05 | 2017-11-05 | 2.5 | 2017-11-05 | 2017-11-05 | Pradnya Shukla | Completed
|  |  |  | Code Peer Review | 2 | 2017-11-05 | 2017-11-05 | 3 | 2017-11-05 | 2017-11-05 | Priyanka Chaudhary | Completed
|  |  |  | Peer Testing | 1 | 2017-11-06 | 2017-11-06 | 2.5 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Naveen | Completed
|  |  |  | Rework | 2 | 2017-11-06 | 2017-11-06 | 1.5 | 2017-11-06 | 2017-11-06 | Rahul Vishwakarma | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 2 | 2017-11-07 | 2017-11-07 | Pradnya Shukla | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Pratik Potdar | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 2.5 | 2017-11-07 | 2017-11-07 | Rahul Vishwakarma | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 2 | 2017-11-08 | 2017-11-08 | Naveen | Completed
|  |  |  | Total Planned Hrs : | 66.6 |  | Total Actual Hrs: | 74 |  |  |  | Completed
Library Management System | 3 | Add Book | Analysis | Requirement Analysis | 1.5 | 2017-11-01 | 2017-11-01 | 1.5 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 1.8 | 2017-11-01 | 2017-11-01 | 1.8 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2017-11-02 | 2017-11-02 | 0.7 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Rahul Vishwakarma | N/A
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Priyanka Chaudhary | N/A
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pradnya Shukla | N/A
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Aditi Dumbre | N/A
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Naveen | N/A
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 |  | 2017-11-04 | 2017-11-04 | Pratik Potdar | N/A
|  |  | Build | Coding | 12 | 2017-11-04 | 2017-11-04 | 14.5 | 2017-11-04 | 2017-11-04 | Naveen | Completed
|  |  |  | Code Self Review | 5 | 2017-11-04 | 2017-11-04 | 5 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Self Testing | 6 | 2017-11-05 | 2017-11-05 | 5.5 | 2017-11-05 | 2017-11-05 | Pratik Potdar | Completed
|  |  |  | Rework | 3 | 2017-11-05 | 2017-11-05 | 4 | 2017-11-05 | 2017-11-05 | Pradnya Shukla | Completed
|  |  |  | Code Peer Review | 2 | 2017-11-05 | 2017-11-05 | 2.5 | 2017-11-05 | 2017-11-05 | Rahul Vishwakarma | Completed
|  |  |  | Peer Testing | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Priyanka Chaudhary | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Rework | 2 | 2017-11-06 | 2017-11-06 | 2 | 2017-11-06 | 2017-11-06 | Naveen | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 3.6 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 5 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 1 | 2017-11-08 | 2017-11-08 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Total Planned Hrs : | 66.7 |  | Total Actual Hrs: | 51.3 |  |  |  | Completed
Library Management System | 4 | Remove Book | Analysis | Requirement Analysis | 1.8 | 2017-11-01 | 2017-11-01 | 1.8 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2017-11-01 | 2017-11-01 | 2.4 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.9 | 2017-11-02 | 2017-11-02 | 0.8 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Pratik Potdar | N/A
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Aditi Dumbre | N/A
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Priyanka Chaudhary | N/A
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pradnya Shukla | N/A
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Naveen | N/A
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 |  | 2017-11-04 | 2017-11-04 | Rahul Vishwakarma | N/A
|  |  | Build | Coding | 10 | 2017-11-04 | 2017-11-04 | 10 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Code Self Review | 2 | 2017-11-04 | 2017-11-04 | 2.5 | 2017-11-04 | 2017-11-04 | Naveen | Completed
|  |  |  | Self Testing | 5 | 2017-11-05 | 2017-11-05 | 5.5 | 2017-11-05 | 2017-11-05 | Pratik Potdar | Completed
|  |  |  | Rework | 1 | 2017-11-05 | 2017-11-05 | 1.5 | 2017-11-05 | 2017-11-05 | Priyanka Chaudhary | Completed
|  |  |  | Code Peer Review | 1 | 2017-11-05 | 2017-11-05 | 1 | 2017-11-05 | 2017-11-05 | Pradnya Shukla | Completed
|  |  |  | Peer Testing | 1 | 2017-11-06 | 2017-11-06 | 1.75 | 2017-11-06 | 2017-11-06 | Rahul Vishwakarma | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1.25 | 2017-11-06 | 2017-11-06 | Naveen | Completed
|  |  |  | Rework | 1 | 2017-11-06 | 2017-11-06 | 2 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 3 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 3.2 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 1 | 2017-11-08 | 2017-11-08 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Total Planned Hrs : | 57.7 |  | Total Actual Hrs: | 39.9 |  |  |  | Completed
Library Management System | 5 | Issue Book | Analysis | Requirement Analysis | 2.1 | 2017-11-01 | 2017-11-01 | 2.1 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.1 | 2017-11-01 | 2017-11-01 | 2.1 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2017-11-02 | 2017-11-02 | 0.8 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Priyanka Chaudhary | N/A
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Naveen | N/A
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Aditi Dumbre | N/A
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pratik Potdar | N/A
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Rahul Vishwakarma | N/A
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 |  | 2017-11-04 | 2017-11-04 | Pradyna Shukla | N/A
|  |  | Build | Coding | 13 | 2017-11-04 | 2017-11-04 | 10 | 2017-11-04 | 2017-11-04 | Naveen | Completed
|  |  |  | Code Self Review | 5 | 2017-11-04 | 2017-11-04 | 5 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Self Testing | 6 | 2017-11-05 | 2017-11-05 | 6.6 | 2017-11-05 | 2017-11-05 | Priyanka Chaudhary | Completed
|  |  |  | Rework | 3 | 2017-11-05 | 2017-11-05 | 3.2 | 2017-11-05 | 2017-11-05 | Pradyna Shukla | Completed
|  |  |  | Code Peer Review | 2 | 2017-11-05 | 2017-11-05 | 3 | 2017-11-05 | 2017-11-05 | Rahul Vishwakarma | Completed
|  |  |  | Peer Testing | 2 | 2017-11-06 | 2017-11-06 | 2.8 | 2017-11-06 | 2017-11-06 | Pratik Potdar | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1.5 | 2017-11-06 | 2017-11-06 | Naveen | Completed
|  |  |  | Rework | 2 | 2017-11-06 | 2017-11-06 | 2.5 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 3.5 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 2 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 4.5 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 1 | 2017-11-08 | 2017-11-08 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Total Planned Hrs : | 69.6 |  | Total Actual Hrs: | 51.8 |  |  |  | Completed
Library Management System | 6 | Return Book | Analysis | Requirement Analysis | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.1 | 2017-11-01 | 2017-11-01 | 2.1 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.9 | 2017-11-02 | 2017-11-02 | 0.9 | 2017-11-02 | 2017-11-02 | Anoop Singh Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Aditi Dumbre | N/A
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Naveen | N/A
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Priyanka Chaudhary | N/A
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pratik Potdar | N/A
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Rahul Vishwakarma | N/A
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 |  | 2017-11-04 | 2017-11-04 | Pradnya Shukla | N/A
|  |  | Build | Coding | 10 | 2017-11-04 | 2017-11-04 | 11.3 | 2017-11-04 | 2017-11-04 | Naveen | Completed
|  |  |  | Code Self Review | 2 | 2017-11-04 | 2017-11-04 | 2.5 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Self Testing | 5 | 2017-11-05 | 2017-11-05 | 5 | 2017-11-05 | 2017-11-05 | Priyanka Chaudhary | Completed
|  |  |  | Rework | 1 | 2017-11-05 | 2017-11-05 | 1 | 2017-11-05 | 2017-11-05 | Rahul Vishwakarma | Completed
|  |  |  | Code Peer Review | 1 | 2017-11-05 | 2017-11-05 | 1 | 2017-11-05 | 2017-11-05 | Pradnya Shukla | Completed
|  |  |  | Peer Testing | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Pratik Potdar | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Naveen | Completed
|  |  |  | Rework | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 4 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 4 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 2 | 2017-11-08 | 2017-11-08 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Total Planned Hrs : | 56.8 |  | Total Actual Hrs: | 40.2 |  |  |  | Completed
| 7 | Check Grant Status | Analysis | Requirement Analysis | 1.5 | 2017-11-01 | 2017-11-01 | 2.7 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.1 | 2017-11-01 | 2017-11-01 | 2.1 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2017-11-02 | 2017-11-02 | 0.8 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Aditi Dumbre | N/A
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Priyanka Chaudhary | N/A
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pradnya Shukla | N/A
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Rahul Vishwakarma | N/A
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Naveen | N/A
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 |  | 2017-11-04 | 2017-11-04 | Pratik Potdar | N/A
|  |  | Build | Coding | 6 | 2017-11-04 | 2017-11-04 | 6 | 2017-11-04 | 2017-11-04 | Naveen | Completed
|  |  |  | Code Self Review | 2 | 2017-11-04 | 2017-11-04 | 2.5 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Self Testing | 4 | 2017-11-05 | 2017-11-05 | 4.5 | 2017-11-05 | 2017-11-05 | Priyanka Chaudhary | Completed
|  |  |  | Rework | 1 | 2017-11-05 | 2017-11-05 | 1.5 | 2017-11-05 | 2017-11-05 | Naveen | Completed
|  |  |  | Code Peer Review | 1 | 2017-11-05 | 2017-11-05 | 1 | 2017-11-05 | 2017-11-05 | Pradnya Shukla | Completed
|  |  |  | Peer Testing | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Rahul Vishwakarma | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Pratik Potdar | Completed
|  |  |  | Rework | 1 | 2017-11-06 | 2017-11-06 | 1.5 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 3.5 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 4.5 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 1.5 | 2017-11-08 | 2017-11-08 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Total Planned Hrs : | 52 |  | Total Actual Hrs: | 36.3 |  |  |  | Completed
Library Management System | 8 |  | Analysis | Requirement Analysis | 2.1 | 2017-11-01 | 2017-11-01 | 3 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2017-11-01 | 2017-11-01 | 2.4 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Anoop Singh Jaswal, Rahul Yadav, Prabhjot Singh, Pritika Sharma, Balaji Veerappan ,Nafeez Virani | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.9 | 2017-11-02 | 2017-11-02 | 1 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Priyanka Chaudhary | N/A
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Naveen | N/A
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Aditi Dumbre | N/A
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Rahul Vishwakarma | N/A
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pradyna Shukla | N/A
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 |  | 2017-11-04 | 2017-11-04 | Pratik Potdar | N/A
|  |  | Build | Coding | 10 | 2017-11-04 | 2017-11-04 | 11 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Code Self Review | 4 | 2017-11-04 | 2017-11-04 | 3.5 | 2017-11-04 | 2017-11-04 | Naveen | Completed
|  |  |  | Self Testing | 6 | 2017-11-05 | 2017-11-05 | 6 | 2017-11-05 | 2017-11-05 | Rahul Vishwakarma | Completed
|  |  |  | Rework | 2 | 2017-11-05 | 2017-11-05 | 2 | 2017-11-05 | 2017-11-05 | Pradnya Shukla | Completed
|  |  |  | Code Peer Review | 2 | 2017-11-05 | 2017-11-05 | 2 | 2017-11-05 | 2017-11-05 | Priyanka Chaudhary | Completed
|  |  |  | Peer Testing | 1.5 | 2017-11-06 | 2017-11-06 | 2 | 2017-11-06 | 2017-11-06 | Naveen | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Rework | 1.5 | 2017-11-06 | 2017-11-06 | 2 | 2017-11-06 | 2017-11-06 | Pradnya Shukla | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 3 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 3.5 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 2 | 2017-11-08 | 2017-11-08 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Total Planned Hrs : | 64 |  | Total Actual Hrs: | 46.6 |  |  |  | Completed
Survey Management System | 9 | Create,Edit User Details | Analysis | Requirement Analysis | 1.8 | 2017-11-01 | 2017-11-01 | 1.8 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2017-11-01 | 2017-11-01 | 2.4 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Preparing QFB | 1.2 | 2017-11-01 | 2017-11-01 | 1.2 | 2017-11-01 | 2017-11-01 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2017-11-02 | 2017-11-02 | 0.8 | 2017-11-02 | 2017-11-02 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Aditi Dumbre | N/A
|  |  |  | LLD Preparation | 5 | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Naveen | N/A
|  |  |  | UTP Review | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Rahul Vishwakarma | N/A
|  |  |  | UTP Rework | 2 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pratik Potdar | N/A
|  |  |  | LLD Review | 2.5 | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Pradyna Shukla | N/A
|  |  |  | LLD Rework | 2.5 | 2017-11-04 | 2017-11-04 |  | 2017-11-04 | 2017-11-04 | Priyanka Chaudhary | N/A
|  |  | Build | Coding | 11 | 2017-11-04 | 2017-11-04 | 9 | 2017-11-04 | 2017-11-04 | Naveen | Completed
|  |  |  | Code Self Review | 3 | 2017-11-04 | 2017-11-04 | 2 | 2017-11-04 | 2017-11-04 | Aditi Dumbre | Completed
|  |  |  | Self Testing | 6 | 2017-11-05 | 2017-11-05 | 6 | 2017-11-05 | 2017-11-05 | Pratik Potdar | Completed
|  |  |  | Rework | 2 | 2017-11-05 | 2017-11-05 | 2 | 2017-11-05 | 2017-11-05 | Naveen | Completed
|  |  |  | Code Peer Review | 2 | 2017-11-05 | 2017-11-05 | 2 | 2017-11-05 | 2017-11-05 | Pradyna Shukla | Completed
|  |  |  | Peer Testing | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Rahul Vishwakarma | Completed
|  |  |  | Test Result review | 1 | 2017-11-06 | 2017-11-06 | 1 | 2017-11-06 | 2017-11-06 | Aditi Dumbre | Completed
|  |  |  | Rework | 2 | 2017-11-06 | 2017-11-06 | 2 | 2017-11-06 | 2017-11-06 | Naveen | Completed
|  |  |  | Code Integration | 3 | 2017-11-07 | 2017-11-07 | 3.2 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Integration Testing | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Rework | 4 | 2017-11-07 | 2017-11-07 | 3 | 2017-11-07 | 2017-11-07 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Test Result review | 1.4 | 2017-11-08 | 2017-11-08 | 2 | 2017-11-08 | 2017-11-08 | Pratik Potdar, Pradnya Shukla, Rahul Vishwakarma, Naveen Gownivaripalli, Priyanka Chaudhary, Aditi Arun Dumbre | Completed
|  |  |  | Total Planned Hrs : | 63.6 |  | Total Actual Hrs: | 40.4 |  |  |  | Completed
|  |  |  | Tot Planned Hrs | 552.6 |  | Tot Act Hrs | 418.7